## FEEDBACK
Recommendation | Current Action [any measures currently being taken to address the recommendation] | Planned Action [future actions that will be implemented to meet the recommendation] | Challenges [potential risks or difficulties and strategies to overcome them] | Priority (high/medium/low) [urgency assigned to the recommendation] | Responsible Person/Team [Name/Department] | Timeline [expected completion date]
1. Establish long-term funding for community-based mental health services. | The ICB has a long-standing contract with South London and Maudsley NHS Foundation Trust (SLaM) that includes the provision of community-based mental health services. This is supplemented by national funding to address emerging community needs. Alongside this, long-term funding for community-based mental health services is also established and maintained via procurement of contracts for services in the community. The Council and ICB separately and jointly fund community-based supported accommodation provision in the borough, a Wellbeing Hub and numerous smaller grants and contracts providing employment support, peer support and meaningful activities. | Partnership Southwark is committed to enhancing community mental health services through integrated and coordinated efforts. Their ambition is to ensure that adults who need mental health support can access it easily and without long waits. This includes improving equity of access, enhancing mental health support on a neighbourhood level, and addressing long waiting times for neurodevelopmental disorder diagnoses. The commitment to these priorities aligns with the recommendations for establishing long-term arrangements for community-based mental health services, ensuring a holistic and accessible approach to mental health care for all residents. | The demand for acute and specialist services impacts our ability to invest further in community-based mental health services. SLaM is in a challenged financial position, as are the ICB and the local authority. Officers are addressing this by taking action to address spend on specialist services and will seek to maximise available funding for the communtiy. | Medium | The Director of Integrated Commissioning will be responsible for a continued assessment of its proportion of spending in the VCSE sector through various funding streams. The Director for Partnership Sustainability will be respondible for refreshing Partnership Southwark strategic priority focusing on Adult Mental Health. This work will incorporate priority spend areas and providing support for the VCSE. | Ongoing, In line with Joint Forward Plan 2023-2028
2. Utilise the current Creative Health programme hosted by South East London Integrated Care Board to implement targeted projects for Black Men. | The SEL Creative Health Network is convened across local authority Public Health and Culture teams at borough level, along with input from the ICB. A main feature of the local programme is the Southwark Culture Health and Wellbeing Partnership (SCHWeP), a network of creative health providers. Mental health is one of SCHWeP's three priority areas. Separate from the Creative Health programme, Partnership Southwark have funded SEL Mind to provide the Black River Counselling service specifically for Black men. This funding has been extended from the Health Inequalities Fund while SEL Mind seeks longer-term funding. | The Council and SCHWeP will lead three round-table discussions at a conference hosted by SEL ICB in February 2025. The aim of these discussions will be to co-produce actionable recommendations that relate to the priority areas and inform a wider programme of work aiming to establish Southwark as London's first "Creative Health Borough." Consideration of this recommendation will form part of these discussions. | The ICB and the Council must consider a range of funding needs in the context of a challenging financial situation, including provision of statutory services. Officers will seek to mitigate this by exploring opportunities to develop culturally competent and bespoke provision within future procurement opportunities. | Medium | Southwark Council and SCHWeP will lead three round-table discussions at a conference hosted by SEL ICB on February 12th. These discussions will aim to produce actionable recommendations related to mental health, reducing inequalities and culturally appropriate service provision. SCHWeP, SEL ICB, Public Health, and Partnership Southwark, will review the outcomes of these round-table discussions. The insights gained will be evaluated against other priorities for the 2025/26 period or placed on a suitable waitlist for future implementation. Commissioners will continue to ensure that our universally accessible services, such as SEL Mind, the Wellbeing Hub, and Community Southwark grant-funded VCSE provisions, are inclusive and responsive to the needs of all community members. | On-going Q4 24/25 - Q1 25/6 Q4 24/25 - Q1 25/6 On-going
3. Provide training and support for VCS groups and community leaders. | The Public Health department's current mental health training programme has successfully targeted and trained numerous community and faith organisations. This training includes mental health first aid and mental health literacy, and these efforts will continue to be a priority. | Public Health will maintain its leadership role in this area, ensuring that their training offerings are widely distributed and accessible. The report (pages 36-39) highlights the importance of utilising ordinary access points, such as barbershops, places of worship, and gyms, to support better awareness campaigns and facilitate conversations about mental health. Public Health will monitor the uptake of training in these venues to ensure broad community engagement and impact. By providing targeted training and support to VCS groups and community leaders, we aim to enhance mental health awareness and literacy across diverse community settings, fostering a more informed and supportive environment for all residents. | Engaging private and independent contractors in mental health training presents several challenges. One significant barrier is the potential loss of income for these individuals due to the time spent in training sessions. To address this, it is essential to consider the timing of the training sessions and possibly provide reasonable reimbursement to offset any financial impact. Additionally, there is no immediate guarantee that residents will seek out the trained individuals for support, which may affect the perceived value of the training. Furthermore, without ongoing support networks, these individuals may feel less confident in their knowledge and ability to apply their training effectively. | High | Southwark Council Public Health | Ongoing, in line with Joint Forward Plan 2023-2028
4. Facilitate cross-sector collaboration. | There are a range of forums operating in Southwark at a strategic level to support cross-sector collaboration on mental health, including the Health and Wellbeing Board and the local care partnership (Partnership Southwark.) Within Partnership Southwark, there is a LIve Well group, focused on mental health. Alongside this, leaders from the Council, the ICB, SLAM, primary care, and the voluntary sector meet through the local Community Mental Health Delivery Group. This group oversees community mental health transformation locally, including the development of joint working across different agencies and the voluntary sector. The ICB and SLAM have invested in roles to enable clinical leads to contribute to cross-sector transformation and collaboration. | We are currently in the process of refreshing the Live Well and Community Mental Health Delivery Group aims, objectives, membership, and ways of working. | There are a range of competing pressures on professionals' time which can pose a challenge in being able to contirbute to cross-sector working. Officers will mitigate this by securing senior buy in to partnership working arrangements to ensure they are appropriately prioritised and resourced. | High | The Integrated Commissioning and Partnership Southwark teams are leading on the refresh of joint working arrangements, with partners from SLAM, primary care, the local authority, and the volunary sector. | Q4 24/25 - Q1 25/26
5. Embed the Patient and Carer Race Equality Framework (PCREF) across all mental health services. | This work is taken forward by SLaM and is outside of scope for the ICB. For their part SLaM has initiated the PCREF approach Patient and Carer Race Equality Framework (PCREF). The 3 stakeholder groups for this include services users & carers, the community (facilitated through Black Thrive) & staff. In Southwark, the following activities outcome measures have emerged: -- Reducing seclusion -- Reducing restrictive practice -- Reducing violence and aggression -- Reducing the number of complaints. | SLaM will meet the objectives outlined by: -- Having trained PCREF inpatient champions -- Holding quarterly roadshows for staff, service users, carers and the local community -- A monthly co-learning group with inpatient ward managers, senior managers and PCREF triple leadership members -- 6 monthly PCREF network meetings | N/A, please see SLaM submission. | High | SLaM | On-going / see SLaM submission.
6. Commission a ‘Taster Day’ event for community-based mental health services and use learnings to support the implementation of Recommendation 2. | No current action in relation to this recommendation. | The development of a 'Taster Day' or equivalent event is a welcome idea, and this recommendation will be taken forward by SEL ICB and Partnership Southwark. | There are a range of competing pressures on professionals' time which can pose a challenge . Officers will mitigate this by planning collaboratively, asking partners to prioritise, and appropriately resourcing. | Medium | SEL ICB commissioners and Partnership Southwark will consider development of a 'Taster Day' or equivalent public-facing event bringing together mental health services in Southwark. | Q1 - Q3 25/26
7. Consultation with non-clinical and community-based mental health services to identify needs and establish good practice models. | Officers from Integrated Commissioning regularly engage with non-clinical services to identify needs and discuss service provision. For example the Integrated Commissioning Team have recently been consulting with non-clinical and community-based mental health services while conducting a review of Southwark's Wellbeing Hub service, ahead of its re-procurement in the summer of 2025. The review has explored good practice models for universally accessible 'hub' services, health inequalities, inclusivity, and the continuation and/or development of targeted initiatives provided by the Hub. The review aims to ensure that the Wellbeing Hub continues to meet the diverse needs of the community effectively and equitably. | See above action on refreshing community mental health joint working arrangements - this will include relevant non-clinical and voluntary sector representation. Additionally, officers from the Integrated Commissioning team intend to regularly attend Mental Health Working Group meetings facilitated by Community Southwark on an on-going basis. | N/A - officers do not foresee challenges in meeting this recommendation. | High | The Integrated Commissioning team will take this recommendation forward and partners will benefit from non-clinical and voluntary sector input at the relevant forums. | On-going
8. Implement a targeted mental health awareness campaign for Black men. | No current action in relation to this recommendation. | The development of a black men's campaign is a welcome idea. Officers will work together with partners including Community Southwark to identify messaging and resourcing to enable this. Alongside this, Public Health will ensure that its "5 Ways to Wellbeing" campaign is culturally competent and accessible to all population groups, with targeted approaches to reach communities facing the greatest health inequalities . This will be achieved by collaborating with our community health ambassadors, including social prescribers, as highlighted in recent reports. | Officers want to maximise the effectiveness and impact of any campaign - to support this officers will seek to co-produce with the the community, and colleagues from across our mental health partnerships. | Medium | Public Health SEL ICB | TBC TBC